## Estimator
Effort
a = the best-case estimate | 3 | D
m = the most likely estimate | 7 | D
b = the worst-case estimate | 9 | D
Time
Resource Effectiveness | 100% | D
Budgeted Time on Task | 8.6667
Duration
Resource Availability | 85% | D
Duration of Task | 10.1961
Calculations
Weighted Estimate (E) | 6.6667
Standard Deviation (SD) | 1
Confidence Level (C) | + | -
68% | 7.6667 | 5.6667
90% | 8.3117 | 5.0217
95% | 8.6667 | 4.6667
99.7% | 9.6667 | 3.6667
Based on the assumption (possibly unwarranted) that a double-triangular distribution governs the data, several estimates are possible. These values are used to calculate an E value for the estimate and a standard deviation (SD) as L-estimators, where:
E = (a + 4m + b) / 6
SD = (b − a) / 6
E is a weighted average which takes into account both the most optimistic and most pessimistic estimates provided. SD measures the variability or uncertainty in the estimate. In Project Evaluation and Review Techniques (PERT) the three values are used to fit a Beta distribution for Monte Carlo simulations.
The triangular distribution is also commonly used. It differs from the double-triangular by its simple triangular shape and the mode does not have to coincide with the median. The mean (expectation) is then:
E = (a + m + b) / 3. In some applications, the triangular distribution is used directly as an estimated probability distribution, rather than for the derivation of estimated statistics.
To produce a project estimate the project manager:
* Decomposes the project into a list of estimable tasks, i.e. a work breakdown structure
* Estimates the E value and SD for each task.
* Calculates the E value for the total project work as E (Project Work) = Σ E (Task)
* Calculates the SD value for the total project work as SD (Project Work) = √(Σ SD (Task) )
* The E and SD values are then used to convert the project estimates to confidence levels as follows:
C =
Confidence level in E value +/- SD is approximately 68%
Confidence level in E value +/- 1.645 × SD is approximately 90%
Confidence level in E value +/- 2 × SD is approximately 95%
Confidence level in E value +/- 3 × SD is approximately 99.7%
Information Systems typically use the 95% confidence level, i.e. E Value + 2 × SD, for all project and task estimates.
These confidence level estimates assume that the data from all of the tasks combine to be approximately normal (see asymptotic normality). Typically, there would need to be 20–30 tasks for this to be reasonable, and each of the estimates E for the individual tasks would have to be unbiased.
Industry average availabiity is 85%, in the absence of other information.
David Shaw